## Product Backlog
Product Name:	Khadka Robot Shop					Fields in blue expect your input!
Team ID:	Prabesh Khadka

Name:	Prabesh Khadka
Initials:	PK
Student ID:	1001201007

(Additional names for teams only)
Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Total Features	Left	Available	Completed	Sprint Ends
Total at Start	32	32
Sprint 1	32	32	1	Mar 28
Sprint 2	31	32	3	Apr 04
Sprint 3	29	32	7	Apr 11
Sprint 4	25	32	9	Apr 18
Sprint 5	23	32	10	Apr 25
Sprint 6	22	32	11	May 02

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Sprint # (by team size)					Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID	Prio	Status	Actual Sprint #	1	2	3	4	Pts	Cml	As a...	I want to...	So that...	Type	Notes
Create Parts	1	CO	1	1	1	1	1	21	21	PM	create robot parts	I can define robot models	CLI	No menu required here – run program, create a part
Create Model	2	CO	2	2	1	1	1	13	34	PM	define new robot models	RRS can sell them to our Beloved Customers	CLI	Menu needed – create parts, then create a robot model
Browse Catalog	3	CO	2	2	1	1	1	5	39	BC	browse a catalog of robot models	I can buy one or more robots	CLI	Need to list robots models, then list parts in selected model
New Customer	4	CO	3	3	2	1	1	3	42	PB	create a new Beloved Customer	I can keep track of who's buying our products	CLI	The usual name, customer number, phone number, and email address
Sales Agent	5	CO	3	3	2	1	1	3	45	PB	create a new Sales Associate	I can keep track of my employees' performance	CLI	Name and employee number at a minimum
Create Order	6	CO	3	3	2	2	1	8	53	SA	create a robot order for a Customer	I can sell robots and thus do my job well	CLI	Select robot model and quantity, show details with total price
Create File	7	CO	3	3	2	2	2	13	66	PB	ensure persistence of the RRS data	we don't lose orders or historical data	CLI	(CLI) Write the data to the default filename and reload it next time the program runs
Create GUI	8	CO	4	4	3	2	2	3	69	All	open a GUI main window	I can interact with RRS Manager with my mouse	GUI	No menu required here – run program, create a part
GUI_Create_parts	9	CO	4	4	3	2	2	34	103	PM	create robot parts via GUI dialogs	I can define robot models	GUI	An fl_input centric approach is OK initially, but a custom dialog is worth bonus points (perhaps Create > Robot Part)
GUI_Create_model	10	NS	5	5	4	3	3	21	124	PM	define new robot models via GUI dialogs	RRS can sell them to our Beloved Customers	GUI	Similar to robot parts (perhaps Create > Robot Model)
GUI_Browse_Catalog	11	NS		6	4	3	3	8	132	BC	browse a catalog of robots via a GUI report	I can buy one or more robots	GUI	A text output is OK initially, but an attractive HTML-like output is desired (perhaps Report > All Robot Models)
	12	NS			5	4	3	21	153	SA	create a robot order for a Customer via GUI	I can sell robots and thus do my job well	GUI	As with CLI (and you’ll need the CLI to add BC and SA people)
	13	NS			5	4	4	13	166	PB	manage a robot order for a Customer via GUI	I can ensure the robot is built and ships	GUI	This will involve a state machine implementation
	14	NS			5	4	4	8	174	PB	create a new Beloved Customer via GUI	I can keep track of who's buying our products	GUI	The usual name, address, phone number, and email address (perhaps Create > Customer)
	15	NS			5	4	4	5	179	PB	create a new Sales Associate via GUI	I can keep track of my employees' performance	GUI	Name and employee number at a minimum (perhaps Create > Sales Associate)
	16	NS			6	5	4	13	192	BC	see pictures of the robots in the GUI catalog	I can see what I'm buying	GUI	Add picture when defining robot model, and show it in the robot model report
	17	NS			6	5	4	5	197	PB	allow the users to save data explicitly via GUI	we can save data without exiting the program	GUI	Write the data to the default filename on command (perhaps File > Save to the default filename)
	18	NS			6	5	4	8	205	PB	allow the users to load data explicitly via GUI	we can manage multiple stores in different files	GUI	Read the data from a user-selected file on command (perhaps File > Open)
	19	NS			6	5	4	8	213	PB	allow the users to save data to a specified name via GUI	we can manage multiple stores in different files	GUI	Write the data to a user-selected file on command and make that fie the default (perhaps File > Save As)
	20	NS				5	5	13	226	PB / SA	view a report of orders per SA in the GUI	I can estimate the value of employees / / I can justify a raise	GUI	A basic text report is fine (perhaps Report > Orders by Sales Associate)
	21	NS				6	5	21	247	All	enable basic login by role and customize the GUI	we don't have options that don't apply to our roles	GUI	User ID might be “sa” for Sales associate with a default password, via a dialog on launch (i.e., in main()),and then make inapplicable menu items inactive – keep it simple
	22	NS				6	5	13	260	All	enable copy and paste from text fields	we can save typing	GUI	Just implement this where the toolkit supports it – not all text widgets do, but it's easy where it's supported
	23	NS				6	6	13	273	BC	view my bill (invoice) in the GUI	I can pay for my robots	GUI	A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Invoice)
	24	NS					6	8	281	BC	view my orders in the GUI	see what I have coming to me	GUI	A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Orders by Customer)
	25	NS					6	8	289	SA	view a sales report in the GUI	I can justify a raise	GUI	A basic text report is fine (perhaps Report > Orders by Sales Associate)
	26	NS					6	8	297	PB	view a report of all orders in the GUI	I can manage the company	GUI	A basic text report is fine (perhaps Report > All Orders)
	27	NS					6	13	310	All	Add multi-level undo	Worry less about making mistakes	GUI	This would be for each Create event (e.g., a new Customer) only (perhaps Edit > Undo)
	28	NS					21	331	BC	see a pie chart of a model's component costs	I can decide if I want a different model	GUI	Consider using Fl_Chart, q.v., (perhaps Report > Robot Model Cost Breakdown)
	29	NS					13	344	SA	create a bulk (2+) order for Customer via GUI	avoid proliferation of orders and paperwork	GUI	Allow more than one robot model (with respective quantity) on a single order
	30	NS					8	352	PM	hide robot parts via GUI	obsolete parts aren't accidentally used	GUI	Mark robot parts as “obsolete” and don't allow adding them to new robot models
	31	NS					8	360	PM	hide robot models via GUI	obsolete robots aren't ordered	GUI	Mark robot models as “obsolete” and don't allow adding them to new orders
	32	NS					21	381	SA	save a draft order and return to it later via GUI	I can multi-task between indecisive customers	GUI	Save an order that hasn't been complete, and allow SA to resume work on it later
Product Backlog Burn Chart
Sprints
Features Remaining at Start of Sprint

## Sprint 01 Backlog
Sprint #	1				***SPRINT 1***
Start on	03/21/17 08:00 AM
End on	03/28/17 08:00 AM
Demo on

Total Tasks	18
Day 1 Left	18
Day 2 Left	17
Day 3 Left	15
Day 4 Left	13
Day 5 Left	7
Day 6 Left	5
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	Create Parts	Architecture	UML	PK	Create a use case diagram	CO
2	Create Parts	Architecture	UML	PK	Create a class diagram	CO
3	Create Parts	Robot_part	Code	PK	Add methods to the parts	CO
4	Create Parts	menu	Code	PK	Create menu option	CO
5	Create Parts	Robot_part	Test	PK	Create main and test the code	CO
6	Create Parts	Head	Code	PK	Create a class for head	CO
7	Create Parts	Head	Code	PK	Compile the code along with the main	CO
8	Create Parts	Head	Test	PK	Test the code	CO
9	Create Parts	Battery	Code	PK	Create a class for battery	CO
10	Create Parts	Battery	Test	PK	Test the code	CO
11	Create Parts	Arms	Code	PK	Create a class for arms	CO
12	Create Parts	Arms	Code	PK	Combine arm class with robot parts	CO
13	Create Parts	Arms	Test	PK	Test the code	CO
14	Create Parts	Torso	Code	PK	Write a class for torso	CO
15	Create Parts	Torso	Test	PK	Test the code	CO
16	Create Parts	Locomoter	Code	PK	Write a class for Locomoter	CO
17	Create Parts	Locomoter	Test	PK	Test the code	CO
18	Create Parts	Wrap_up	Delivery	PK	Finalize the code	CO	Submit the first sprint to blackboard
Sprint Burn Chart
Tasks
Days

## Sprint 02 Backlog
Sprint #	2				***SPRINT 2***
Start on	03/28/17 08:00 AM
End on	04/04/17 08:00 AM
Demo on

Total Tasks	15
Day 1 Left	15
Day 2 Left	13
Day 3 Left	12
Day 4 Left	9
Day 5 Left	7
Day 6 Left	3
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	Create Model	Architecture	UML	PK	Create a use case diagram	CO
2	Create Model	Architecture	UML	PK	Create a class diagram	CO
3	Create Model	new_model	Code	PK	Add model to the code	CO
4	Create Model	new_model	Code	PK	Update the menu option for PM	CO
5	Create Model	new_model	Test	PK	test the code for funtionality	CO
6	Create Model	view_model	Code	PK	create an option to view created model	CO
7	Create Model	view_model	Code	PK	update the menu option for PM	CO
8	Create Model	view_model	Test	PK	Test the code	CO
9	Browse Catalog	Customers	Code	PK	Create a login option for beloved customer	CO
10	Browse Catalog	Customers	Code	PK	Combine the menu option with the customer	CO
11	Browse Catalog	Customers	Test	PK	Test the code	CO
12	Browse Catalog	Browse_catalog	Code	PK	Create menu option to view catalog	CO
13	Browse Catalog	Browse_catalog	Code	PK	Update the menu option for Customer	CO
14	Browse Catalog	Browse_catalog	Test	PK	Test the code	CO
15	Browse Catalog	Main	Delivery	PK	Finalize the code	CO	Submit the second sprint to blackboard
Sprint Burn Chart
Tasks
Days

## Sprint 03 Backlog
Sprint #	3				***SPRINT 3***
Start on	04/04/17 08:00 AM
End on	04/11/17 08:00 AM
Demo on

Total Tasks	19
Day 1 Left	17
Day 2 Left	15
Day 3 Left	12
Day 4 Left	11
Day 5 Left	7
Day 6 Left	3
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	UML	Architecture	UML	PK	Create and update a use case diagram	CO
2	UML	Architecture	UML	PK	Save the use case in .xmi format	CO
3	UML	Architecture	UML	PK	Create and update class diagram	CO
4	UML	Architecture	UML	PK	Save the class diagram in .xmi format	CO
5	New Customer	Customers	Code	PK	create a new customers	CO
6	New Customer	Customers	Code	PK	Update the code in order to save the created customer	CO
7	New Customer	Customers	Test	PK	test the code for functionality	CO
8	Sales Agent	SA	Code	PK	Create a new SA	CO
9	Sales Agent	SA	Code	PK	Create an option to login as new SA	CO
10	Sales Agent	SA	Test	PK	Test the code	CO
11	Create Order	Orders	Code	PK	Write a code to create new orders	CO
12	Create Order	Orders	Code	PK	Update the code for orders and combine it with menu option	CO
13	Create Order	Orders	Test	PK	Test the code	CO
14	Create File	Files	Code	PK	Create default files to store robot parts	CO
15	Create File	Files	Code	PK	Create default file to store robot model	CO
16	Create File	Files	Code	PK	Create default file to store SA, PM’s log	CO
17	Create File	Files	Test	PK	Test the validity of created files	CO
18	Create File	Wrap_up	Test	PK	Read the saved history	CO
19	Create File	Main	Delivery	PK	Finalize the code	CO	Submit the third sprint to the blackboard
Sprint Burn Chart
Tasks
Days

## Sprint 04 Backlog
Sprint #	4				***SPRINT 4***
Start on	04/11/17 08:00 AM
End on	04/18/17 08:00 AM
Demo on

Total Tasks	20
Day 1 Left	15
Day 2 Left	14
Day 3 Left	12
Day 4 Left	11
Day 5 Left	7
Day 6 Left	3
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	UML	Architecture	UML	PK	Create and update a use case diagram	CO
2	UML	Architecture	UML	PK	Save the use case in .xmi format	CO
3	UML	Architecture	UML	PK	Create and update class diagram	CO
4	UML	Architecture	UML	PK	Save the class diagram in .xmi format	CO
5	GUI	GUI	Code	PK	Create a GUI Window	CO
6	GUI	GUI	Code	PK	Create window for Create_parts	CO
7	GUI	GUI	Test	PK	test the code for functionality	CO
8	GUI Create_parts	GUI	Code	PK	Create GUI for Head	CO
9	GUI Create_parts	GUI	Test	PK	Test the code	CO
10	GUI Create_parts	GUI	Code	PK	Create GUI for Arm	CO
11	GUI Create_parts	GUI	Test	PK	Test the code	CO
12	GUI Create_parts	GUI	Code	PK	Create a GUI for Torso	CO
13	GUI Create_parts	GUI	Test	PK	Test the code	CO
14	GUI Create_parts	GUI	Code	PK	Create a GUI for locomoter	CO
15	GUI Create_parts	GUI	Test	PK	Test the code	CO
16	GUI Create_parts	GUI	Code	PK	Create a GUI for Battery	CO
17	GUI Create_parts	GUI	Test	PK	Test the code	CO
18	GUI Create_parts	Files	Test	PK	Test the validity of created files	CO
19	GUI Create_parts	Wrap_up	Test	PK	Read the saved history	CO
20	GUI Create_parts	Main	Delivery	PK	Finalize the code	CO	Submit the fourth sprint to the blackboard
Sprint Burn Chart
Tasks
Days

## Sprint 05 Backlog
Sprint #	5				***SPRINT 5***
Start on	04/18/17 08:00 AM
End on	04/25/17 08:00 AM
Demo on

Total Tasks	21
Day 1 Left	17
Day 2 Left	14
Day 3 Left	14
Day 4 Left	13
Day 5 Left	10
Day 6 Left	5
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	UML	Architecture	UML	PK	Create and update a use case diagram	CO
2	UML	Architecture	UML	PK	Save the use case in .xmi format	CO
3	UML	Architecture	UML	PK	Create and update class diagram	CO
4	UML	Architecture	UML	PK	Save the class diagram in .xmi format	CO
5	GUI	GUI	Code	PK	Update the GUI window	CO
6	GUI	GUI	Code	PK	Update and create window for Create_parts	CO
7	GUI	GUI	Code	PK	Create a class for create models	CO
8	GUI	GUI	Test	PK	test the code for functionality	CO
9	GUI Create_models	GUI	Code	PK	Create GUI window for create robot models	CO
10	GUI Create_models	GUI	Test	PK	Test the code	CO
11	GUI Create_models	GUI	Code	PK	Define inputs for creating model	CO
12	GUI Create_models	GUI	Test	PK	Test the code	CO
13	GUI Create_models	GUI	Code	PK	Create a GUI displaying a dialog box for new models	CO
14	GUI Create_models	GUI	Test	PK	Test the code	CO
15	GUI Create_models	GUI	Code	PK	Create a csv file to store the input data for robot model	CO
16	GUI Create_models	GUI	Test	PK	Test the code	CO
17	GUI Create_models	GUI	Code	PK	Create a message box displaying the data entered including total cost	CO
18	GUI Create_models	GUI	Test	PK	Test the code	CO
19	GUI Create_models	Files	Test	PK	Test the validity of created files	CO
20	GUI Create_models	Wrap_up	Test	PK	test the final code for the sprint	CO
21	GUI Create_models	Main	Delivery	PK	Finalize the code	CO	Submit the fifth sprint to the blackboard
Sprint Burn Chart
Tasks
Days

## Sprint 06 Backlog
Sprint #	5				***SPRINT 6***
Start on	04/25/17 08:00 AM
End on	05/02/17 08:00 AM
Demo on

Total Tasks	21
Day 1 Left	17
Day 2 Left	14
Day 3 Left	14
Day 4 Left	13
Day 5 Left	10
Day 6 Left	5
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	UML	Architecture	UML	PK	Create and update a use case diagram	CO
2	UML	Architecture	UML	PK	Save the use case in .xmi format	CO
3	UML	Architecture	UML	PK	Create and update class diagram	CO
4	UML	Architecture	UML	PK	Save the class diagram in .xmi format	CO
5	GUI	GUI	Code	PK	Update the GUI window	CO
6	GUI	GUI	Code	PK	Update and create window for Create_parts	CO
7	GUI	GUI	Code	PK	Create a class for create models	CO
8	GUI	GUI	Test	PK	test the code for functionality	CO
9	GUI Create_models	GUI	Code	PK	Create GUI window for create robot models	CO
10	GUI Create_models	GUI	Test	PK	Test the code	CO
11	GUI Create_models	GUI	Code	PK	Define inputs for creating model	CO
12	GUI Create_models	GUI	Test	PK	Test the code	CO
13	GUI Create_models	GUI	Code	PK	Create a GUI displaying a dialog box for new models	CO
14	GUI Create_models	GUI	Test	PK	Test the code	CO
15	GUI Create_models	GUI	Code	PK	Create a csv file to store the input data for robot model	CO
16	GUI Create_models	GUI	Test	PK	Test the code	CO
17	GUI Create_models	GUI	Code	PK	Create a message box displaying the data entered including total cost	CO
18	GUI Create_models	GUI	Test	PK	Test the code	CO
19	GUI Create_models	Files	Test	PK	Test the validity of created files	CO
20	GUI Create_models	Wrap_up	Test	PK	test the final code for the sprint	CO
21	GUI Create_models	Main	Delivery	PK	Finalize the code	CO	Submit the fifth sprint to the blackboard
Sprint Burn Chart
Tasks
Days